## Sheet1
☑ = milestone D = deliverable | Week 1 (27/02) | Week 2 (03/02) | Week 3 (10/02) | Week 4 (17/02) | Week 5 (24/02) | Week 6 (03/03) | Week 7 (10/03) | Week 8 (17/03) | Week 9 (24/03) | Week 10 (31/03) | Week 11 (07/04) | Week 12 (14/03)
Initial plan | ☑ D
Background reading |  | ☑
Implementation - Research |  | ☑ | ☑
Implementation - Preprocessing |  |  |  | ☑ ☑ D
Implementation - Clustering |  |  |  |  | ☑ | ☑ D
Implementation - Visualisation | [6 empty] | ☑
Implementation - Correlation | [7 empty] | ☑ D
Testing | [8 empty] | ☑
Analysis | [9 empty] | ☑
Report | [11 empty] | ☑ D